## Risk Register
Risk ID | Risk Description | Risk Category | Likehood | Impact | Risk Score | Risk Level | Risk Treatment | Risk Owner | Status
R-001 | Former employees may gain unauthorized access to company systems due to delayed account deactivation. | Access Control | 3 | 4 | 12 | Medium | Close accounts immediately after employee termination | IT | Open
R-002 | Employee accounts without MFA may be compromised, potentially leading to unauthorized access to company systems and sensitive information. | Access Control | 3 | 5 | 15 | High | Enable MFA for all employee accounts and monitor MFA enrollment | IT | Open
R-003 | Unpatched systems may be exploited by attackers, leading to unauthorized access, data loss, or service disruption. | Vulnerability Management | 3 | 4 | 12 | Medium | Regularly apply security patches and establish a patch management process to ensure systems are updated within defined timeframes. | IT | Open
R-004 | Backups may fail when needed, leading to data loss and service disruption. | Backup & Recovery | 4 | 5 | 20 | High | Regularly test backup restoration and document the test results. | IT | Open
R-005 | Unencrypted devices may expose sensitive data if a device is lost or stolen. | Data Protection / Endpoint Security | 4 | 5 | 20 | High | Enable disk encryption on all company devices and ensure encryption is properly configured. | IT | Open
R-006 | Unverified email links may lead to phishing attacks, unauthorized access, and exposure of sensitive data. | Security Awareness / Phishing | 4 | 5 | 20 | High | Provide regular phishing awareness training and conduct simulated phishing exercises for employees. | IT | Open
R-007 | Internet outages may disrupt business operations and prevent employees from accessing critical systems. | Business Continuity / Network Availability | 4 | 4 | 16 | High | Develop a contingency plan for internet outages and establish backup connectivity. | IT | Open
R-008 | Excessive user access may lead to unauthorized changes, accidental data damage, or exposure of sensitive information. | Access Control | 3 | 4 | 12 | Medium | Grant employees only the access required for their job responsibilities and review access rights regularly. | IT | Open
R-009 | Outdated security policies may lead to improper security practices and increase the risk of data loss or unauthorized access. | Policy & Compliance | 4 | 4 | 16 | High | Review and update information security policies regularly and communicate the latest requirements to employees. | IT | Open
R-010 | Third-party vendors may introduce security risks due to insufficient security assessment and monitoring. | Third-Party Risk Management | 3 | 4 | 12 | Medium | Conduct security assessments of third-party vendors before engagement and review them periodically. | IT | Open

## Control Assessment
Control ID | Risk ID | Control Description | Control Type | Control Owner | Frequency | Evidence | Status
C-001 | R-001 | Immediately deactivate employee accounts upon termination or resignation. | Preventive | IT | Upon employee termination | Account deactivation record | Partially Compliant
C-002 | R-002 | Enable MFA for all employee accounts. | Preventive | IT | Continuous | MFA enrollment report | Partially Compliant
C-003 | R-003 | Regularly apply security patches and update systems within defined timeframes. | Preventive | IT | Monthly | Patch management report | Partially Compliant
C-004 | R-004 | Regularly test backup restoration and document the test results. | Detective | IT | Quarterly | Backup restoration test report | Non-Compliant
C-005 | R-005 | Enable disk encryption on all company devices. | Preventive | IT | Continuous | Device encryption status report | Partially Compliant
C-006 | R-006 | Provide regular phishing awareness training and conduct simulated phishing exercises. | Preventive | IT | Quarterly | Phishing training records and simulation results | Non-Compliant
C-007 | R-007 | Maintain backup internet connectivity and a contingency plan for internet outages. | Corrective | IT | Annually | Contingency plan and backup connectivity test records | Non-Compliant
C-008 | R-008 | Grant employees only the access required for their job responsibilities and review access rights regularly. | Preventive | IT | Quarterly | User access review report | Non-Compliant
C-009 | R-009 | Review and update information security policies regularly and communicate the latest requirements to employees. | Preventive | IT | Annually | Approved policy documents and review records | Non-Compliant
C-010 | R-010 | Conduct security assessments of third-party vendors before engagement and review them periodically. | Preventive | IT | Annually | Vendor security assessment report | Non-Compliant

## Compliance Assessmentet1
Requirement ID | Requirement | Related Control | Current State | Evidence | Compliance Status | Gap | Recommendation
CA-001 | Employee accounts should be deactivated immediately upon termination or resignation. | C-001 | An employee account remained active for 3 days after termination. | Account deactivation record | Partially Compliant | Employee accounts are not always deactivated immediately after termination. | Ensure employee accounts are deactivated immediately upon termination or resignation.
CA-002 | All employee accounts should have MFA enabled. | C-002 | MFA is enabled for 80% of employee accounts. | MFA enrollment report | Partially Compliant | 20% of employee accounts do not have MFA enabled. | Enable MFA for all remaining employee accounts and monitor MFA enrollment regularly.
CA-003 | Systems should be regularly updated with security patches within defined timeframes. | C-003 | Some devices have not received security updates for 6 months. | Patch management report | Partially Compliant | Some systems are not being patched within the required timeframe. | Apply security patches regularly and establish defined patching timeframes for all systems.
CA-004 | Backup restoration should be tested regularly to ensure data can be recovered when needed. | C-004 | Backups exist, but there is no recent evidence that restoration has been tested. | Backup restoration test report | Non-Compliant | Backup restoration is not being tested regularly and there is no recent evidence of successful recovery. | Conduct regular backup restoration tests and document the results.
CA-005 | All company devices should have disk encryption enabled. | C-005 | Some company devices do not have disk encryption enabled. | Device encryption status report | Partially Compliant | Some devices remain unencrypted, increasing the risk of data exposure if devices are lost or stolen. | Enable disk encryption on all company devices and regularly monitor encryption status.
CA-006 | Employees should receive regular phishing awareness training. | C-006 | No regular phishing awareness training is provided. | Phishing training records and simulation results | Non-Compliant | Employees are not receiving regular phishing awareness training. | Provide regular phishing awareness training and conduct simulated phishing exercises.
CA-007 | Critical business systems should have contingency measures for internet outages. | C-007 | No clear contingency plan or backup internet connectivity is in place. | Contingency plan and connectivity test records | Non-Compliant | The company lacks adequate measures to maintain access to critical systems during internet outages. | Develop a contingency plan and establish backup internet connectivity.
CA-008 | Employees should have only the access required for their job responsibilities, with regular access reviews. | C-008 | Some employees have excessive access privileges and access rights are not reviewed regularly. | User access review report | Non-Compliant | Excessive access privileges exist and regular access reviews are not performed. | Apply least-privilege access and conduct regular user access reviews.
CA-009 | Information security policies should be reviewed and updated regularly. | C-009 | Security policies have not been reviewed or updated for more than two years. | Approved policy documents and review records | Non-Compliant | Security policies are outdated and have not been reviewed regularly. | Review and update information security policies at least annually and communicate changes to employees.
CA-010 | Third-party vendors should undergo security assessments before engagement and periodically thereafter. | C-010 | No regular security assessment process for third-party vendors is in place. | Vendor security assessment report | Non-Compliant | Third-party vendors are not regularly assessed for security risks. | Establish a formal third-party security assessment process and conduct periodic reviews.

## Gap Register
Gap ID | Requirement ID | Gap Description | Related Risk | Priority | Recommendation | Status
G-001 | CA-001 | Employee accounts are not always deactivated immediately after termination. | R-001 | High | Ensure immediate account deactivation upon termination or resignation. | Open
G-002 | CA-002 | MFA coverage is incomplete across employee accounts. | R-002 | High | Achieve 100% MFA coverage and monitor enrollment. | Open
G-003 | CA-003 | Some systems are not patched within the required timeframe. | R-003 | High | Establish defined patching timeframes and ensure all systems are updated accordingly. | Open
G-004 | CA-004 | Backup restoration is not tested regularly. | R-004 | High | Conduct and document regular backup restoration tests. | Open
G-005 | CA-005 | Some company devices remain unencrypted. | R-005 | High | Enable disk encryption on all company devices and monitor encryption status. | Open
G-006 | CA-006 | Regular phishing awareness training is not provided to employees. | R-006 | High | Implement regular phishing awareness training and simulated phishing exercises. | Open
G-007 | CA-007 | No adequate contingency measures are in place for internet outages. | R-007 | High | Establish backup connectivity and a documented contingency plan. | Open
G-008 | CA-008 | Excessive access privileges exist and regular access reviews are not performed. | R-008 | Medium | Apply least-privilege access and conduct regular access reviews. | Open
G-009 | CA-009 | Security policies are outdated and have not been reviewed regularly. | R-009 | High | Review and update security policies annually. | Open
G-010 | CA-010 | Third-party vendors are not regularly assessed for security risks. | R-010 | Medium | Establish a formal third-party security assessment process. | Open

## Action Plan
Action ID | Gap ID | Action Description | Action Owner | Priority | Due Date | Satus
A-001 | G-001 | Implement immediate account deactivation upon employee termination or resignation. | IT | High | 30 Days | Open
A-002 | G-002 | Enable MFA for all remaining employee accounts and verify full enrollment. | IT | High | 30 Days | Open
A-003 | G-003 | Establish patching timeframes and update all systems that are missing security patches. | IT | High | 30 Days | Open
A-004 | G-004 | Conduct backup restoration tests and document the results. | IT | High | 30 Days | Open
A-005 | G-005 | Enable disk encryption on all company devices and verify encryption status. | IT | High | 30 Days | Open
A-006 | G-006 | Implement regular phishing awareness training and simulated phishing exercises. | IT | High | 30 Days | Open
A-007 | G-007 | Establish backup internet connectivity and document an outage contingency plan. | IT | High | 30 Days | Open
A-008 | G-008 | Remove unnecessary access privileges and conduct regular access reviews. | IT | Medium | 30 Days | Open
A-009 | G-009 | Review, update, approve, and communicate the latest information security policies. | IT | High | 30 Days | Open
A-010 | G-010 | Establish a formal security assessment process for third-party vendors. | IT | Medium | 30 Days | Open